## Version Control
Version Control Sheet
Document Name : |  | Defect Report |  |  | Document Version No: |  | V1.0
Effective Date : |  | 16/03/2018
Author: |  |  | Reviewer: |  |  | Approver:
Raunak Shah |  |  | Jitendra Sen |  |  | Vijaya Arucapalli
| Signature |  |  | Signature |  |  | Signature
Electronic copies valid without signature
Document Revision History
Ver. No | Effective date |  | Nature of Modification
1.0 | 2018-09-03 |  | Added Defect List for 1.0 Sprint 3
1.1 | 13/03/2018 |  | Updated Defect List for 1.0 Sprint 4
1.2 | 15/03/2018 |  | Updated Defect List for 1.1 Sprint 4
1.3 | 16/03/2018 |  | Updated Defect List for 1.1 Sprint 4

## Analysis
| Sprint / Date Range | Total Defects
1.0 Sprint 1
1.0 Sprint 2
| 1.0 Sprint 3 | 14
| 1.0 Sprint 4 | 11
| 1.1 Sprint 4 | 44
69
Sprint | Severity 1 (Critical) | Severity 2 (Major) | Total
1.0 Sprint 3 | 5 | 9 | 14
1.0 Sprint 4 | 5 | 6 | 11
1.1 Sprint 4 | 6 | 38 | 44
| 16 | 53 | 69

## Defect Report (Date Range)
Project Name: Cognizance
Tested By: Raunak & Raksha
Date: 3/16/2018
Application Link: http://18.144.60.207/
Defect ID | Defect Summary | Priority | Fix Version | Defect Status | Found By | Assigned To
ADPQVP2018-369 | Edit users is not working. | Critical | 1.0 Sprint 4 | Done | raksha.deshpande | manish.tripathi
ADPQVP2018-269 | Not able to login in Firefox browser | Critical | 1.0 Sprint 3 | Done | raunak.shah | harish.patidar
ADPQVP2018-271 | Deactivated user can also login into the application | Critical | 1.0 Sprint 4 | Done | raunak.shah | rohan.sahu
ADPQVP2018-360 | Approval process for Manager to Admin fails. | Critical | 1.0 Sprint 3 | Done | raksha.deshpande | rohan.sahu
ADPQVP2018-340 | 'User' I can actually approve my own article even though it has been assigned to other Manage or Admin | Critical | 1.0 Sprint 4 | Done | raunak.shah | rohan.sahu
ADPQVP2018-328 | Type field in Article is not getting modified | Critical | 1.0 Sprint 4 | Done | raunak.shah | rohan.sahu
ADPQVP2018-334 | I as a 'User' can actually edit articles for the Admin or Manager | Critical | 1.0 Sprint 4 | Done | raunak.shah | rohan.sahu
ADPQVP2018-275 | No message on screen if user tries to create a record using an existing email address. Shows an error on console | Major | 1.0 Sprint 3 | Done | raunak.shah | harish.patidar
ADPQVP2018-364 | Dashboard is blur upon loading. | Major | 1.0 Sprint 4 | Done | raksha.deshpande | manish.tripathi
ADPQVP2018-373 | Dashboard title is shown twice on the screen | Major | 1.0 Sprint 4 | Done | raunak.shah | manish.tripathi
ADPQVP2018-372 | Usernames shown under "created by" in dashboard should also have space in between | Major | 1.0 Sprint 4 | Done | raunak.shah | manish.tripathi
ADPQVP2018-267 | Asterisk sign is missing with Description field on create an article page | Major | 1.0 Sprint 4 | Done | raunak.shah | parul.sharma@intimetec.com
ADPQVP2018-268 | Login UI is distorted, its coming at the top position | Major | 1.0 Sprint 3 | Done | raunak.shah | parul.sharma@intimetec.com
ADPQVP2018-270 | Link- User List which is available on Dashboard allows a normal user who do not have right to access User Setting page, to access the page | Major | 1.0 Sprint 3 | Done | raunak.shah | harish.patidar
ADPQVP2018-314 | Incorrect Mail upon deletion of article | Major | 1.0 Sprint 4 | Done | raksha.deshpande | Sachin.Singh
ADPQVP2018-313 | Incorrect Mail upon deletion of article | Major | 1.0 Sprint 4 | Done | raksha.deshpande | Sachin.Singh
ADPQVP2018-282 | Getting Emails in Junk folder which are received in response of user creation | Major | 1.0 Sprint 3 | Done | raunak.shah | Sachin.Singh
ADPQVP2018-285 | Session is not getting expired, expected time is 60min. | Critical | 1.0 Sprint 3 | Done | raunak.shah | harish.patidar
ADPQVP2018-378 | Upon clicking on the article in dashboard its taking to article list page | Critical | 1.1 Sprint 4 | Done | raksha.deshpande | manish.tripathi
ADPQVP2018-368 | When user submits article to admin for review, it is not showing the approve page. | Critical | 1.1 Sprint 4 | Done | raksha.deshpande | manish.tripathi
ADPQVP2018-336 | Not getting an email is response of When an Admin edits/resets Userâ€™s password | Critical | 1.1 Sprint 4 | Done | raunak.shah | Sachin.Singh
ADPQVP2018-370 | Getting two emails in response of forgot password | Critical | 1.1 Sprint 4 | Done | raunak.shah | Sachin.Singh
ADPQVP2018-350 | Manager is not getting an email that an Article is ReASSIGNED to him for review or if the reviewer is changed | Critical | 1.1 Sprint 4 | Done | raunak.shah | Sachin.Singh
ADPQVP2018-356 | Edit option gets wrongly enabled for the Published Articles for the Reviewer. | Critical | 1.1 Sprint 4 | Done | raunak.shah | harish.patidar
ADPQVP2018-330 | When clicked on the description text area it doesn't work -Usability Issue | Major | 1.1 Sprint 4 | Done | raksha.deshpande | harish.patidar
ADPQVP2018-325 | If a user refreshes the page, left navigational pop up gets closed. It should be done only when user closes it manually | Major | 1.1 Sprint 4 | Done | raunak.shah | harish.patidar
ADPQVP2018-366 | published articles are getting displayed in created by me and assigned to me on articles page, it should display only unpublished as it is only for pending approvals. | Major | 1.1 Sprint 4 | Done | raksha.deshpande | harish.patidar
ADPQVP2018-261 | On refreshing the application from User Settings & Article's page it is redirecting to dashboard | Major | 1.1 Sprint 4 | Done | raunak.shah | harish.patidar
ADPQVP2018-351 | "Article-Name" displayed in Deletion email should not be a link, as the article is deleted | Major | 1.1 Sprint 4 | Done | raunak.shah | Sachin.Singh
ADPQVP2018-335 | On Adding a duplicate user it gives an error "Bad Request" and doesn't say anything about user being already exist | Major | 1.1 Sprint 4 | Done | raunak.shah | rakshitraj
ADPQVP2018-333 | If I login as a user and then it is deactivated, I can still Add/Edit/Approve Articles until I am logged in | Major | 1.1 Sprint 4 | Done | raunak.shah | rohan.sahu
ADPQVP2018-312 | Article Approved mail has invalid link | Major | 1.1 Sprint 4 | Done | raksha.deshpande | Sachin.Singh
ADPQVP2018-310 | Mail is not received upon sending for approval | Major | 1.1 Sprint 4 | Done | raksha.deshpande | Sachin.Singh
ADPQVP2018-311 | The article name should be the actual name of article and upon clicking it should take to the article. | Major | 1.1 Sprint 4 | Done | raksha.deshpande | Sachin.Singh
ADPQVP2018-349 | IMPROVEMENT: .docx should be added as supported file type for adding as an attachment | Major | 1.1 Sprint 4 | Done | raunak.shah | manoj.mewara
ADPQVP2018-357 | If a Admin or Manager assigned for reviewing an Article is deactivated. Then in current implementation it is not show in "Assign for Review" field on the edit screen, though it is shown on Article View Page | Major | 1.1 Sprint 4 | Done | raunak.shah | ashish.y
ADPQVP2018-308 | The attachment is failing for .PNG format. | Major | 1.1 Sprint 4 | Done | raksha.deshpande | manoj.mewara
ADPQVP2018-343 | Negative scenario: If a user clicks on Post comment button without any content, then an email is sent with not content. Proper restriction can be applied on UI | Major | 1.1 Sprint 4 | Done | raunak.shah | manish.tripathi
ADPQVP2018-358 | The text on the Button should be Approve instead of Approved. When admin/manager tries to approve. | Major | 1.1 Sprint 4 | Done | raksha.deshpande | manish.tripathi
ADPQVP2018-265 | sorting for "Name", "Email", "Created On", "Status", "Role" fields displayed on 'User Setting' page is failed. | Major | 1.1 Sprint 4 | Done | raksha.deshpande | harish.patidar
ADPQVP2018-381 | Assigned to me should not be displayed on Article list page for a normal user | Major | 1.1 Sprint 4 | Done | raunak.shah | harish.patidar
ADPQVP2018-379 | In my Profile normal user is allowed to change the roles | Major | 1.1 Sprint 4 | Done | raksha.deshpande | manish.tripathi
ADPQVP2018-359 | "Assign to Me" should not be available for a normal User, as we can not assign any article for review to normal user | Major | 1.1 Sprint 4 | Done | raunak.shah | harish.patidar
ADPQVP2018-273 | Password field modification is not working. | Major | 1.0 Sprint 3 | Done | raunak.shah | rohan.sahu
ADPQVP2018-276 | Search with complete User name is not working | Major | 1.0 Sprint 3 | Done | raunak.shah | rohan.sahu
ADPQVP2018-272 | Not able to search using STATUS and DATE field | Major | 1.0 Sprint 3 | Done | raunak.shah | rohan.sahu
ADPQVP2018-374 | Space should be there in between "CreatedBy" field | Major | 1.1 Sprint 4 | Done | raunak.shah | harish.patidar
ADPQVP2018-280 | Time for showing the error message on screen can be increased. For example try login with some wrong credentials. | Major | 1.0 Sprint 3 | Done | raunak.shah | harish.patidar
ADPQVP2018-288 | Error are displayed on console when you are on login screen and also after you logged in into the application | Major | 1.0 Sprint 3 | Done | raunak.shah | harish.patidar
ADPQVP2018-257 | Editing the article is not working | Major | 1.1 Sprint 4 | Done | raksha.deshpande | harish.patidar
ADPQVP2018-329 | "Items per page" selection drop down is not working | Major | 1.1 Sprint 4 | Done | raunak.shah | harish.patidar
ADPQVP2018-342 | Usability Issue: Comment should be displayed to the creator user of an article on view screen, right now it only shows on edit screen | Major | 1.1 Sprint 4 | Done | raunak.shah | manish.tripathi
ADPQVP2018-365 | When clicked on view all pending approvals,it shows all the articles including approved articles. | Major | 1.1 Sprint 4 | Done | raksha.deshpande | harish.patidar
ADPQVP2018-324 | Editing Inactive users give a bad request | Major | 1.1 Sprint 4 | Done | raksha.deshpande | rakshitraj
ADPQVP2018-317 | Last Modified time is incorrect. | Major | 1.1 Sprint 4 | Done | raksha.deshpande | raunak.shah
ADPQVP2018-326 | BreadCrumb is not showing properly. It is showing Dashboard/settings/Users/Edit-user on all places | Major | 1.1 Sprint 4 | Done | raunak.shah | raunak.shah
ADPQVP2018-332 | Article without a description field can be saved from Edit screen | Major | 1.1 Sprint 4 | Done | raunak.shah | raunak.shah
ADPQVP2018-347 | Spinner keeps rotating if user tries to upload an invalid file in article | Major | 1.1 Sprint 4 | Done | raunak.shah | harish.patidar
ADPQVP2018-327 | Allowed files shown on create and Edit screen are different | Major | 1.1 Sprint 4 | Done | raunak.shah | raunak.shah
ADPQVP2018-309 | Proper message to be displayed when invalid format file is attached. | Major | 1.1 Sprint 4 | Done | raksha.deshpande | manish.tripathi
ADPQVP2018-338 | Slider for Side Navigational Panel is not working in Firefox | Major | 1.1 Sprint 4 | Done | raunak.shah | parul.sharma@intimetec.com
ADPQVP2018-262 | UI distortion on creating an article with an image files which is longer in dimensions | Major | 1.1 Sprint 4 | Done | raunak.shah | parul.sharma@intimetec.com
ADPQVP2018-315 | Able to attach more than 10 files. | Major | 1.1 Sprint 4 | Done | raksha.deshpande | manish.tripathi
ADPQVP2018-289 | The KMT prototype application is not getting loaded in IE 11. | Critical | 1.0 Sprint 3 | In Progress | raunak.shah | harish.patidar
ADPQVP2018-290 | The KMT prototype application is not getting loaded in Mac(Safari). It showing a blank screen | Critical | 1.0 Sprint 3 | In Progress | raunak.shah | harish.patidar
ADPQVP2018-345 | If the review name is modified, it is not getting reflected on "Reviewed By" field on VIEW ARTICLE Page | Major | 1.1 Sprint 4 | To Do(Known Limitation) | raunak.shah | raunak.shah
ADPQVP2018-331 | Image can be pasted in description field, which Distorts the View Article page UI | Major | 1.1 Sprint 4 | To Do(Known Limitation) | raunak.shah | raunak.shah
ADPQVP2018-352 | Font type applied in description field text is not shown on View Article Page | Major | 1.1 Sprint 4 | To Do(Known Limitation) | raunak.shah | parul.sharma@intimetec.com
ADPQVP2018-337 | In firefox, filter widget fields are not shown properly | Major | 1.1 Sprint 4 | To Do(Known Limitation) | raunak.shah | harish.patidar